## Sheet1
Step | Task | Description | Duration
1 | Define Project Scope and Requirements | Clearly outline the goals, expected accuracy, and environmental constraints of the system. | 3
2 | Procure Components for System | Purchase ultrasonic transducer, pulser/receiver module, microcontroller (Arduino/Raspberry Pi), and related components. | 7
3 | Design and Simulate Circuit | Use LTspice or other tools to simulate the pulse generator, amplifier, and filtering circuit. | 5
4 | Assemble Pulser/Receiver Circuit | Assemble the components on a breadboard or PCB and verify connections. | 5
5 | Program Microcontroller or Raspberry Pi | Write firmware/software for pulse generation, signal acquisition, and data processing. | 10
6 | Develop and Test Signal Processing Algorithms | Develop and test algorithms for time-of-flight calculation, noise reduction, and thickness computation. | 7
7 | Integrate Components into a Mobile Enclosure | Mount components in a compact, durable enclosure for mobile operation in the field. | 10
8 | Calibrate System with Known Pipe Samples | Use calibration pipes of known thickness and material properties to fine-tune the system. | 7
9 | Field Test System on Recovery Boiler Pipes | Conduct tests on actual recovery boiler pipes, ensuring accuracy and reliability under operational conditions. | 14
10 | Document Results and Develop User Guide | Compile documentation, including calibration data, system setup, and usage instructions. | 7